## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | BMC; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | ARD; 9/30/2020 | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
Capture Pieces | Given that there is an opponent's piece adjacent and in front of a piece, when the piece jumps over it to an empty valid space, then the opponent's piece should be captured and disappear from the board. |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that there is an opponent's piece is in front of a piece then the piece shouldn't be able to jump over and capture their opponent's piece |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that there is an opponent's piece is in behind a piece then the piece shouldn't be able to jump over and capture their opponent's piece |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that the piece the player is trying to jump over is their own piece then the piece shouldn't be able to jump over and capture that piece |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
Make a Move | Given that there is an unoccupied valid space diagonal and in front of a piece, when the piece is selected and moved to that space then the piece should move to it. |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that there is an unoccupied invalid space in front of a piece, when the piece is selected and move that space then the piece should not move. |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that there is an occupied valid space adjacent and in front of a piece, when the piece is selected and moved to that space then the piece should not move. |  |  | Pass | KJM 10/20/2020 | Pass | KJM 11/4/2020
| Given that there is a space, valid or not, unoccupied or occupied, when the piece is selected and moved to that space then the piece should not move. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
| Given that I click submit turn and my turn is valid, then it become my opponents turn. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
| Given that I click backup and I have made a move, then my move is undone. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
Resign Game | Given I am in a game when I click the resign button then the game should end and I should be returned to the home page. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
| Given I am in a game waiting for my turn when my opponent clicks the resign button then I expect to be returned to the home page. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
| Given I am in a game and it is my turn when my opponent clicks the resign button then I expect to receive a message stating that my opponent has resigned and prompting me to return home when I next perform an action. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
King Pieces | Given that my piece has made it to the final row of the board opposite from my side, when it reaches that row then the piece should become a king piece |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
| Given that my piece has become a king, when I move it to any unoccupied valid space in any direction then the piece should move to that space. |  |  | Pass | CAP 10/20/2020 | Pass | KJM 11/4/2020
Review Replay | Given I am on the homepage and at least one game has been completed by anyone when click watch replay on that game's replay then I can review the replay of the game turn-by-turn. |  |  |  |  | Pass | KJM 11/4/2020
| Given I am watching the replay when I click next move then the game proceeds to the next move |  |  |  |  | Pass | KJM 11/4/2020
| Given I am watching the replay when I click previous move then the game proceeds to the previous move |  |  |  |  | Pass | KJM 11/4/2020
| Given the replay is at the last turn when I click next move then nothing happens, and the button appears grayed out |  |  |  |  | Pass | KJM 11/4/2020
| Given the replay is at the first turn of the game when I click previous move then nothing happens, and the button appears grayed out |  |  |  |  | Pass | KJM 11/4/2020
Save Replay | Given that I am playing a game of checkers, when I the game ends then a replay of my game will be saved |  |  |  |  | Pass | KJM 11/4/2020
Updated username requirements | Given I am not signed in when I try to sign in with a name that does not begin with a capital letter then I should not be signed in, and the sign in page should display an error message informing me that usernames must begin with a capital letter. |  |  |  |  | Pass | KJM 11/4/2020
| Given I am not signed in when I try to sign in with a name that ends with a space then I should not be signed in, and the sign in page should display an error message informing me that usernames must not end with spaces. |  |  |  |  | Pass | KJM 11/4/2020
| Given I am not signed in when I try to sign in with a name that contains any characters that are not alphanumeric or spaces then I should not be signed in, and the sign in page should display an error message informing me that usernames must contain only alphanumeric characters and spaces. |  |  |  |  | Pass | KJM 11/4/2020
| Given I am not signed in when I try to sign in with a name that is less than twelve characters in length then I should not be signed in, and the sign in page should display an error message informing me that usernames must be at least twelve characters in length. |  |  |  |  | Pass | KJM 11/4/2020
| Given I am not signed in when I try to sign in with a name that is not already in use, that is at least twelve characters in length, that begins with a capital letter, that does not end with a space, and that does not contain any characters that are not alphanumeric characters or spaces, then I should be signed in and redirected to the home page. |  |  |  |  | Pass | KJM 11/4/2020